## Sheet1
Project Name | Gym Modernization
Project Manager | Akram K.
Start Date | 2018-02-12
End Date | 2018-05-15
Overall Progress | 40%
Tasks | Responsible | Start | End | Days | Status
2018-02-16
Set kick-off meeting | Jay E. | 2018-02-12 | 2018-02-12 | 0 | Complete
Agree on objectives | Akram K. | 2018-02-12 | 2018-02-12 | 0 | Complete
Deliverable 1(Planning)- Perform cost/benefit analysis, assess feasibilities, and select project methodology for Gym Modernization Project
System Request | Jay E. | 2018-02-12 | 2018-02-23 | 11 | Complete
Technical Feasibility Study including any programming or database problems(decided to build web application) | Jay E. & Alek B. | 2018-02-12 | 2018-02-23 | 11 | Complete
Economic Feasibility Study including Cost/Benefit Analysis(server cost, user training fees, etc) | Akram K. & Tom I. | 2018-02-12 | 2018-02-23 | 11 | Complete
Organizational Feasibility Study(Identify users, stakeholders, and any other external entities) | Pk & Daniel C. | 2018-02-12 | 2018-02-23 | 11 | Complete
Full Project Methodology( Agile, Scrum, V-Model, Waterfall?) | All | 2018-02-12 | 2018-02-25 | 13 | Complete
Deliverable 2(Analysis)- Interview Gym Staff and Conduct a Requirements analysis to produce Use Case Documents
Interviews of Marketing Coordinator, Gym member, Personal Trainer, and IT Staff | All | 2018-02-28 | 2018-02-28 | 0 | Complete
Use Case Documents( identified actors, triggers, type, preconditions, and postconditions for each use case) | All | 2018-03-01 | 2018-03-09 | 8 | Complete
Use Case Diagrams for scheduling appointments, online login, payment etc, | All | 2018-03-01 | 2018-03-09 | 8 | Complete
Fix CBA(Numbers needed tweaking. Finished that though group meetings) | Alek B., Akram, Tom | 2018-02-26 | 2018-03-02 | 4 | Complete
Deliverable 3(Design)- Data Flow Diagrams for Gym Modernization Project
Context Diagram( Top down view of our system, consisted of gym member, gym system, receptionist, and personal trainer. Completed during a group meeting on March 28. | All | 2018-03-26 | 2018-03-28 | 2 | Complete
Level 0 Diagram( Further broke down gym system into entrance system, online login system, and TPS). Completed during group meeting on April 4. | All | 2018-03-28 | 2018-04-04 | 7 | Complete
Level 1 Diagram(Entrance system, login system, and TPS each had to be separated into processes. Worked on it as group from April 4-April 6. | All | 2018-04-04 | 2018-04-06 | 2 | Complete
Level 2 Diagram( Every process in Level 1 was broken down and refined even further). Done by group April 6-April 8. Group meeting occured on April 6. | All | 2018-04-06 | 2018-04-08 | 2 | Complete
Powerpoint Presentation explaining each level of our DFD | All | 2018-04-06 | 2018-04-08 | 14 | In-Progress
Appropriate data stores, data flows, processes, and entities labeled clearly | All | 2018-03-26 | 2018-04-08 | 13 | In-Progress
Kanban Board updated with meetings and due dates for diagrams | Akram | 2018-03-26 | 2018-04-09 | 14 | Complete
Deliverable 4(Design cont'n)
ER Diagram | All | 2018-04-09 | 2018-04-20 | 11 | Not-Started
Presentation | All
Deliverable 5(Implementation/Operation)